## Overview
CDPI — AI FDE Delivery Tracker
Cognitive Document Intelligence Platform, mapped to the AI FDE End-to-End Production Delivery Spine
Generated from a direct audit of the repository (code read line-by-line, not assumed) plus the attached AI FDE spine PDF. All secrets found hardcoded during the audit were fixed in this same session — see the Security_Remediation_Log tab.
Tab | What's in it
FDE_Stage_Tracker | All 42 stages of the FDE spine mapped to CDPI's actual current state, target state, owner, and Azure service(s).
Feature_Backlog | 18 stand-out features to build, prioritized, with Azure services and effort.
Azure_Service_Mapping | Every brownfield component mapped 1:1 to its Azure replacement, with cost tier and Azure-for-Students availability.
KPI_Tracker | Before/after KPI framework (per FDE spine Section 3), adapted to CDPI. Most 'Before' values are 'Not yet measured' — no baseline exists today.
Security_Remediation_Log | The secrets found and fixed in this session, plus what's still open (git history).
Vendor_Risk_Register | Third-party dependencies (OpenAI, ElevenLabs, Google Speech, n8n, Gmail) and concentration risk.
Live summary (reads from FDE_Stage_Tracker)
Total stages
Done
In Progress
Not Started
% Complete

## FDE_Stage_Tracker
FDE Stage Tracker
42-stage AI FDE spine mapped to CDPI's current state
# | Stage | Current State in CDPI | Target State / Action | Status | Owner | Azure Service(s)
1 | Engage & Qualify | Undocumented ownership — informal 'Group 3' B.E. project team, no named sponsor. | Define sponsor/owner, scope doc, engagement boundaries. | Not Started | Aditya | —
2 | Stakeholder Discovery | No stakeholder map — TA/business lead/tech eval are just email recipient roles in config. | Document roles: HR/TA, hiring manager, candidate, dev owner. | Not Started | Aditya | Entra ID (roles)
3 | Frame Problem & Value | Problem is implicit: speed up resume screening. No written problem statement. | Write problem statement + success criteria. | Not Started | Aditya | —
4 | Capture Before-AI KPIs | No baseline captured anywhere — no cycle time, cost/hire, or error-rate data exists. | Baseline: manual screening time/resume, cost/hire, before building more features. | Not Started | Aditya | Azure Monitor (future)
5 | Discover Current Process & Brownfield Landscape | Done in this session — full code audit (7 LLM call sites, 5 hardcoded secrets, no tests, no CI). | Documented in this tracker. | Done | Claude/Aditya | —
6 | Root-Cause Analysis | Manual screening is slow/inconsistent; root cause = no structured data store, no semantic matching. | Write a 5-Whys doc for each pain point. | In Progress | Aditya | —
7 | Assess the "Bad" Brownfield Repo | Flat-file storage, 5 hardcoded secrets (now fixed), subprocess-chained scripts, zero tests, no CI, no requirements.txt (now added). | See Security_Remediation_Log + Azure_Service_Mapping. | Done (assessment) | Claude | —
8 | AI-vs-No-AI Qualification | GenAI used for parsing/scoring/questions (justified — unstructured text); rule-based tiering (justified — deterministic); voicebot follow-ups (reconsider — could be scripted/cheaper). | Document a per-feature AI/no-AI decision log. | In Progress | Aditya | —
9 | Define Initial PRD / Product Intent | README.md is the closest thing to a PRD today; no personas, no formal release hypothesis. | Formalize a PRD including the dashboard + WhatsApp-replacement scope. | Not Started | Aditya | —
10 | Choose Target Architecture + ADRs | No target architecture or ADRs exist. | This workbook's Azure_Service_Mapping sheet + the architecture diagram are the first ADR-equivalent. | In Progress | Aditya | Multiple — see Azure_Service_Mapping
11 | Define Data, Knowledge & Context Strategy | No data contracts; flat CSV/JSON files with no schema, no lineage, no retrieval layer. | /context-lake scaffolding created this session (schemas + container design). | In Progress | Claude | Cosmos DB, Blob Storage
12 | Spec-Driven Design | Code-first throughout — no specs written before implementation anywhere in the repo. | Write specs for the dashboard + semantic search before building either. | Not Started | Aditya | —
13 | Requirements → Specs → Tests → Evidence Traceability | No traceability matrix; zero automated tests found anywhere in the repo. | This tracker is the first traceability artifact — extend it per feature as built. | Not Started | Aditya | —
14 | Create Transformation / Migration Plan | No migration plan exists; brownfield components have no documented path to target state. | Azure_Service_Mapping sheet serves as the migration plan (component-by-component). | In Progress | Claude | —
15 | Transform Bad Repo → Good Repo | Secrets removed from code this session; still no package structure, no shared app/service layer, no tests. | Refactor scripts into packages, add pytest, add CI. | In Progress | Aditya | GitHub Actions
16 | Validate the Good Repo | No quality gate exists yet. | Add pytest + lint + security scan (e.g. Bandit/Trivy) as a merge gate. | Not Started | Aditya | GitHub Actions, Defender for Cloud
17 | Refine / Finalise PRD | N/A until target architecture is locked. | Revisit after Stage 10/12 land. | Not Started | Aditya | —
18 | Plan Evidence-Driven Delivery | No formal backlog existed before this session. | Feature_Backlog sheet in this workbook is the first sprint-ready backlog. | Done (backlog) | Aditya | Azure Boards (optional)
19 | Build Intelligence Core | 7 LLM prompts live (GPT-3.5-turbo via LangChain), zero embeddings/RAG/retrieval anywhere. | /prompts library created (versioned, exact source text) this session; /semantic-library designed. | In Progress | Claude | Azure AI Foundry, Azure AI Search
20 | Build Application & Services | 7 standalone scripts chained via subprocess; no shared API layer; no frontend exists. | Build an API layer (FastAPI/Azure Functions) + the requested frontend dashboard. | Not Started | Aditya | Azure Functions, Azure Static Web Apps
21 | Integrate with Enterprise Systems | Gmail IMAP polling every 60s, SMTP sending, scripts invoked via subprocess.call. | Event-driven integration: Blob trigger, Logic Apps connectors instead of polling. | Not Started | Aditya | Azure Event Grid, Logic Apps
22 | Engineer Agent / Tool / Decision Intelligence | Rule-based tiering (top/mid/bottom 25%) in ResumeMEtrics.py; no agent or tool-calling anywhere. | Keep deterministic tiering as-is; add bounded tool-calling only for semantic-search queries. | Not Started | Aditya | —
23 | Engineer HITL + Deterministic Control Boundaries | "To be Considered" tier is de-facto HITL today, but informal — just an emailed CSV. | Formal review queue in the dashboard (approve/reject UI, logged decision). | Not Started | Aditya | —
24 | Security + Privacy + Responsible AI by Design | 5 hardcoded secrets found & fixed this session; resume PII stored unencrypted on local disk/in CSV; scoring-weight fairness never reviewed. | Key Vault for all secrets; encryption at rest (Blob/Cosmos default); fairness review of scoring_config.json weights. | In Progress | Claude/Aditya | Azure Key Vault
25 | Governance + Compliance + Assurance | No AI registry, no model card, no compliance mapping exists. | Write a model card for the scoring logic + voicebot scoring prompt. | Not Started | Aditya | —
26 | TEVV + AI Red Teaming | Zero automated tests of any kind confirmed in the audit — no golden/edge/adversarial cases. | Build a golden/edge/adversarial resume test set before any further AI feature work. | Not Started | Aditya | —
27 | Production Harden | No IaC, no CI/CD, no RBAC anywhere; secrets were in source until this session. | Bicep/Terraform + GitHub Actions + Entra ID RBAC. | Not Started | Aditya | Bicep, GitHub Actions
28 | Engineer Reliability & Resilience | Single bare try/except per LLM call site, no retry/backoff, no fallback model, no circuit breaker. | Add retry+backoff, a fallback model, and an AI-disabled degraded mode. | Not Started | Aditya | —
29 | AI Incident Response + BC/DR | No AI incident playbook exists; hallucination/prompt-injection/outage scenarios undocumented. | Define a playbook for hallucination, prompt injection, and provider outage. | Not Started | Aditya | —
30 | Release / Cutover / Rollback | No deployment exists at all today — everything runs locally. | Stage the rollout: Blob/Cosmos first (lowest risk), then compute, then frontend. | Not Started | Aditya | —
31 | Observability + SLO/SLA Engineering | log.txt is 20,000+ lines of freeform text; no metrics, traces, or alerts anywhere. | Application Insights + dashboards — this also becomes the frontend dashboard's data source. | Not Started | Aditya | Azure Monitor, App Insights
32 | Token Economics + AI FinOps + TCO | No token or cost tracking exists for any of the 7 LLM call sites. | Log tokens per call; build a cost-per-resume dashboard. | Not Started | Aditya | Azure Cost Management
33 | Vendor / Third-Party / Concentration Risk | 4 vendor dependencies (OpenAI, ElevenLabs, Google Speech, lost-access n8n) with zero fallback for any. | See Vendor_Risk_Register sheet. | Done (register) | Claude | Azure AI Foundry, Azure AI Speech
34 | Measure After-AI KPIs | Cannot measure 'after' without a 'before' baseline (Stage 4 is not done yet). | Pending Stage 4. | Not Started | Aditya | —
35 | Before-vs-After Variance + Value Leakage | N/A until Stage 4 and 34 exist. | Pending. | Not Started | Aditya | —
36 | ROI / NPV / Benefits Realisation | N/A until KPI baseline/after data exists. | Pending. | Not Started | Aditya | —
37 | Define Operating Model + RACI + Ownership | Informal "Group 3" team, every row in this tracker's Owner column is currently a single person — single point of failure. | Formal RACI once the team/scope is confirmed beyond one person. | In Progress | Aditya | —
38 | Handover + Knowledge Transfer | README.md was the only artifact before this session. | This tracker + /prompts + /context-lake + /semantic-library = handover pack v1. | In Progress | Claude | —
39 | Drift + Continuous Improvement | No drift monitoring or prompt-version history existed before this session. | /prompts/registry.json is the first version-tracking step. | In Progress | Claude | —
40 | Scale / 90-Day Transformation Roadmap | N/A — first use case not yet in production. | Prompt library, context-lake schema, and semantic-index design are already reusable across any future JD/role type. | Not Started | Aditya | —
41 | Retirement / Decommissioning | The n8n WhatsApp automation is already informally "retired" (lost access) with zero documented retirement criteria or archival. | Write a retirement checklist; apply it retroactively to the lost n8n flow for a clean paper trail. | Not Started | Aditya | —
42 | Executive Defence & Final Value Story | README.md is the closest artifact; no measurable value story exists yet. | Build once KPIs exist (Stage 34-36 complete). | Not Started | Aditya | —

## Feature_Backlog
Feature Backlog
Stand-out features to build, prioritized P0 (now) -> P2 (later)
Feature | Description | Category | Priority | Azure Service(s) | Effort | Status | Notes
Recruiter/Admin Frontend Dashboard | Live pipeline funnel, candidate rankings, interview status, cost/token usage in one UI. | Frontend | P0 | Azure Static Web Apps + Azure Functions API + Entra ID auth | L | Not Started | Directly requested; also serves as the Stage 31 observability UI.
WhatsApp Candidate Notifications | Rebuild the lost n8n flow: interview invites/reminders/status updates via WhatsApp. | Integration | P0 | Azure Logic Apps + WhatsApp Business Cloud API (or re-host n8n on Azure Container Apps) | M | Not Started | See Azure_Service_Mapping 'n8n WhatsApp' row — removes a single point of failure.
Centralized Context Lake | One queryable source of truth for candidates/interviews/scores/audit instead of 5 scattered file trees. | Data | P0 | Azure Cosmos DB, Azure Blob Storage | M | Design done | See /context-lake; blocks both the dashboard and semantic search.
Secrets in Key Vault | Move all API keys/passwords out of .env/config.json entirely. | Security | P0 | Azure Key Vault + Managed Identity | S | Partially Done | Today's fix (env/config lookups) is step 1; Key Vault is step 2.
Semantic Resume-to-JD Matching (RAG) | Replace the LLM's free-text 'JD Match %' guess with retrieval-grounded matching. | AI/Backend | P1 | Azure AI Search, Azure AI Foundry embeddings | M | Design done | See /semantic-library.
Prompt Library with Versioning | Externalize and version all 7 LLM prompts instead of inline f-strings. | AI/Governance | P1 | Repo-based now; Azure App Configuration later | S | Done | See /prompts.
Human Review Queue | Structured approve/reject UI for the 'To Be Considered' tier instead of just an emailed CSV. | Product | P1 | Part of the frontend dashboard | M | Not Started | Formalizes FDE Stage 23 (HITL).
Event-Driven Pipeline | Blob upload auto-triggers parsing; removes the 60s poll loop and subprocess.call chaining. | Backend | P1 | Azure Event Grid, Azure Functions | M | Not Started | Replaces file_watcher.py's polling model.
Structured Observability + Token/Cost Dashboard | Replace freeform log.txt with real traces, metrics, and per-call token logging. | Ops | P1 | Azure Monitor, Application Insights | M | Not Started | Feeds the frontend dashboard directly.
Automated Test Suite | Golden / edge / adversarial resume cases — zero tests exist today. | Quality | P1 | GitHub Actions CI | M | Not Started | Blocks safe refactoring of anything else on this list.
Bias/Fairness Audit of Scoring Weights | scoring_config.json weights (industry penalty, culture fit, etc.) have never been reviewed for bias. | Responsible AI | P1 | Azure AI Content Safety / manual audit | S | Not Started | FDE Stage 24 gap.
Retry/Fallback for LLM Calls | No retry logic exists anywhere — one failed call silently skips a candidate. | Reliability | P1 | — | S | Not Started | FDE Stage 28 gap.
CI/CD Pipeline | No automated build/test/deploy exists today. | DevOps | P1 | GitHub Actions, Bicep/Terraform | M | Not Started | —
Structured JSON Output | Replace free-text 'return clean JSON' prompting with schema-enforced structured outputs. | AI Quality | P1 | Azure AI Foundry structured outputs | S | Not Started | Fixes the brittle json.loads() parsing noted in the prompt library README.
Azure AI Speech for TTS/STT | Replace ElevenLabs + Google Speech with one Azure-native service. | AI | P2 | Azure AI Speech | S | Not Started | Reduces vendor concentration risk (FDE Stage 16).
Multi-JD / Multi-Tenant Support | Score candidates against multiple concurrent JDs/roles — today only the single most-recent JD file is used. | Product | P2 | Cosmos DB (jd-corpus), Azure AI Search | L | Not Started | See /semantic-library/index_schema.json jd-corpus index.
Role-Based Access Control for Dashboard | Recruiter vs hiring manager vs exec views. | Security | P2 | Microsoft Entra ID | S | Not Started | —
Embedded Analytics for Exec Reporting | Funnel conversion, time-to-hire, DEI metrics. | Analytics | P2 | Power BI Embedded or Azure Workbooks | M | Not Started | Serves FDE Stage 42 (Executive Defence).

## Azure_Service_Mapping
Azure Service Mapping
Every brownfield component -> its Azure replacement, with cost tier and Azure-for-Students availability
Brownfield Component (Current) | Azure Replacement | Why / How | Cost Tier | Azure-for-Students Available?
InputResume_Folder / OutputResume_Folder (local disk) | Azure Blob Storage | Durable, triggers Event Grid on upload, geo-redundant. | Low (pay-per-GB) | Yes
file_watcher.py (watchdog polling + 60s Gmail poll) | Azure Event Grid + Azure Functions (Blob trigger) | Event-driven instead of polling; scales to zero when idle. | Low (consumption plan) | Yes
subprocess.call(["python","ResumeParser.py"]) chaining | Azure Functions / Azure Container Apps Jobs | Proper async invocation with retries, not shelling out to a whole script. | Low | Yes
resume_summary.csv, candidate_ranking_metrics.csv | Azure Cosmos DB (NoSQL API) | Queryable, supports partial updates, feeds the dashboard directly. | Low (serverless tier) | Yes (free tier)
config/*.json + .env (secrets) | Azure Key Vault + Managed Identity | No secrets in code or config files at all; access via identity, not keys. | Low | Yes
Gmail IMAP polling (imaplib) | Azure Logic Apps (Gmail connector) or Microsoft Graph webhook | Event-driven, no 60s poll loop, built-in retry. | Low | Yes (consumption)
smtplib SMTP email sending | Azure Communication Services — Email | Managed deliverability, no app-password management. | Low | Yes
Manually generated .ics calendar invites | Microsoft Graph Calendar API | Native Outlook/Teams calendar integration with RSVP tracking. | Low | Yes (M365 dev tenant)
OpenAI GPT-3.5-turbo (direct API via LangChain) | Azure AI Foundry Models (GPT-4o-mini / GPT-4o) | Same LangChain integration (ChatOpenAI -> AzureChatOpenAI); adds data residency + Azure RBAC. | Medium (token-based) | Needs approval — keep direct OpenAI as interim
No semantic search (string/keyword matching only) | Azure AI Search (vector + hybrid) | See /semantic-library/index_schema.json. | Low (Basic tier) | Yes
No vector embeddings anywhere | Azure AI Foundry text-embedding-3-small | Powers the AI Search vector field. | Low (token-based) | Needs approval — fallback: OpenAI embeddings API directly
ElevenLabs TTS (hardcoded key, 3rd party) | Azure AI Speech (Neural TTS) | One fewer vendor; native Azure billing/quota. | Low | Yes
Google Web Speech API (speech_recognition, STT) | Azure AI Speech (Speech-to-Text) | Same vendor as TTS above; streaming support. | Low | Yes
log.txt (20,000+ line freeform text file) | Azure Monitor + Application Insights | Structured, queryable (KQL), alerting, feeds dashboards. | Low (pay-per-GB ingested) | Yes
No frontend / no dashboard | Azure Static Web Apps (React/Next.js) + Azure Functions API | Free tier, built-in CI/CD from GitHub, Entra ID auth built in. | Free tier available | Yes
No authentication/RBAC anywhere | Microsoft Entra ID | Free tier covers up to 50k MAU — easily enough for a student project. | Free | Yes
n8n WhatsApp automation (lost access, not in repo) | Azure Logic Apps + WhatsApp Business Cloud API, or re-host n8n on Azure Container Apps | Direct Logic Apps integration removes the n8n dependency entirely; re-hosting n8n is faster if old flows must be reused as-is. | Low either way | Yes
No infrastructure-as-code / manual setup | Bicep (Azure-native IaC) | Version-controlled infrastructure; matches the 'Good Repo' criteria in the FDE spine. | Free (only resources it provisions cost money) | Yes
No CI/CD | GitHub Actions + Azure deployment | Free minutes for public/student repos. | Free tier | Yes
PyInstaller .exe / build artifacts committed to git (dist/, build/) | Azure Container Apps (containerized deployment) | Removes committed build binaries from git entirely; standard container build in CI instead. | Low | Yes

## KPI_Tracker
Before / After KPI Tracker
Per FDE spine Section 3 — adapted to CDPI. Most 'Before' values read 'Not yet measured' because no baseline exists today; that gap is Stage 4 of the tracker.
KPI Family | Before (Current State) | After (Target, once instrumented) | Data Source
Cycle Time | Not yet measured — no timestamped baseline of manual screening time per resume exists. | P50/P95 time from resume upload to ranked tier, per candidate. | Application Insights trace
Manual Effort | Not yet measured — FTE hours per resume not tracked. | Human review effort retained only for the 'To be Considered' tier. | Dashboard review-queue logs
Decision Quality | Not yet measured — no ground truth / hiring-outcome labels linked back to scores. | Model accuracy vs. actual hire outcome, override rate by reviewers. | Cosmos DB scoring_history + hire outcomes
Audit Coverage | None — log.txt is freeform text, not queryable evidence. | 100% of scoring decisions traceable via audit_log container. | Cosmos DB audit_log
Reliability | Not yet measured — no uptime/error-rate tracking exists for any script. | Availability %, error rate, recovery time once Functions/Event Grid pipeline is live. | Azure Monitor
Latency | Not yet measured — no per-call timing captured. | P50/P95/P99 latency for parse-to-score pipeline. | Application Insights
Scalability | Unknown — single-threaded local script, no load testing ever performed. | Validated concurrent-resume throughput under Functions autoscaling. | Load test results
Security Posture | 5 hardcoded secrets found this session (now fixed); no RBAC, no Key Vault. | Least-privilege via Managed Identity, zero secrets in source, Key Vault-only access. | Security_Remediation_Log tab
Cost per Case | Not yet measured — no token or infra cost tracking exists. | Cost per successfully scored candidate (tokens + infra + storage). | Azure Cost Management + token logs
Token Usage | Not tracked at all — no logging of input/output tokens on any of the 7 LLM call sites. | Tokens per resume/interview/question-set, tracked per prompt (see /prompts registry). | App-level token logging -> App Insights
TCO | Not modeled — GPT-3.5-turbo + ElevenLabs + local compute costs never aggregated. | AI platform + inference + infrastructure + people + ops, consolidated model. | Azure Cost Management
Adoption / Automation Rate | Not yet measured — unclear what % of candidates are fully auto-processed vs. need manual intervention. | % automated end-to-end vs. requiring human review. | Dashboard pipeline funnel
Business Value | Not modeled — no cost-of-manual-screening baseline to compare against. | ROI/NPV once baseline + after-KPIs both exist (Stages 4, 34-36). | Executive Defence doc (Stage 42)

## Security_Remediation_Log
Security Remediation Log
What was found and fixed in this session (FDE Stage 24 evidence)
Item | File(s) | Issue | Action Taken | Status | Residual Risk
OpenAI API key (primary) | .env | Live key committed in plaintext. | Untracked from git (already in .gitignore). | Done | Still in git history — rotate at platform.openai.com regardless.
OpenAI API key (duplicated in source) | ResumeParser.py, generate_questions.py, voicebot/voice_bot.py | Same key hardcoded directly in 3 source files. | Replaced with os.environ lookup via python-dotenv; fails fast with a clear error if missing. | Done | Same underlying key as above — one rotation fixes all 4 locations.
Gmail app password | config/email_credentials.json, file_watcher.py | Live app password in plaintext in 2 locations. | Untracked config file + env var lookup (GMAIL_WATCHER_USER/PASSWORD) added to code. | Done | Rotate the Gmail app password.
ElevenLabs API key | voicebot/config.json, voicebot/elevenlabs_utils.py | Live key in plaintext in 2 locations. | Untracked config file + code now actually reads from config.json (was unused/dead before). | Done | Rotate the ElevenLabs key.
Example/template files | .env.example, config/email_credentials.json.example, voicebot/config.json.example | No templates existed — fresh clone had no way to know what to configure. | Created placeholder templates. | Done | —
Git history | All of the above | Old keys remain in prior commits; may already be public if this repo was ever pushed to GitHub. | Not addressed — requires history rewrite + force-push, deferred for now. | Open | Recommend git filter-repo + force-push + rotate all keys regardless of whether history is rewritten.

## Vendor_Risk_Register
Vendor / Concentration Risk Register
Per FDE spine Section 16
Vendor | Used For | Dependency Risk | Portability | Azure-Native Alternative | Notes
OpenAI | LLM — parsing, scoring, interview questions, voicebot (7 call sites) | High | Medium (LangChain abstracts the provider) | Azure AI Foundry Models | Needs Azure OpenAI/Foundry approval on the student subscription.
ElevenLabs | Text-to-speech for the voicebot | Medium | High | Azure AI Speech | Low switching cost; key was hardcoded, now fixed.
Google (Web Speech API via speech_recognition) | Speech-to-text for the voicebot | Medium | High | Azure AI Speech | Free tier has undocumented rate limits for production use; consolidate with ElevenLabs replacement.
n8n (self-hosted, access lost) | WhatsApp candidate notifications | High | Low (flow logic unrecovered) | Azure Logic Apps + WhatsApp Business Cloud API | Rebuild from scratch; document before formally 'retiring' per FDE Stage 41.
Gmail / IMAP | Resume ingestion + interview slot download | Medium | Medium | Microsoft Graph / Azure Communication Services | Consumer Gmail account used for business automation with legacy app-password auth.